## Change Order
PROJECT: |  |  |  | CHANGE ORDER NO.:
SITE LOCATION:
DSA No.: |  |  |  | CHANGE ORDER DATE:
DSA File No.:
RCCD P.O. #:
CONTRACTOR: |  |  |  | CONTRACT FOR: | o | New Construction
ADDRESS: |  |  |  |  | o | Renovation/Modernization
[5 empty] | o | Scheuled Maintenance
[5 empty] | o | System Upgrades
ARCHITECT: |  |  |  |  | o | Addition
ADDRESS: |  |  |  |  | o | Other: ________________
ADJUSTMENT IN CONTRACT SUM |  |  |  | ADJUSTMENT IN CONTRACT TIME
Original Contract Sum: |  |  |  | Original Contract Time: |  |  | days
Prior Adjustments: |  |  | #DIV/0! | Prior Adjustments: |  |  | days
Adjustment for this Change: |  |  | #DIV/0! | Adjustments for this Change: |  |  | days
Revised Contract Sum: |  | 0 | #DIV/0! | Revised Completion Days: |  |  | days
This Change Order represents a full and final compensation for all cost, direct and indirect, associated with the work and time agreed herein, including but not limited to, all costs incurred for extended overhead, disruption or suspension of work, labor inefficiencies, and the change’s impact on the unchanged work. This includes all known and unknown claims against RCCD (Owner), Soltek (Contractor) and the Project, including but not limited to, disputed, undisputed and doubtful claims. Payment by RCCD of the amount agreed under this Change Order shall constitute a full and complete accord and satisfaction of all such claims and shall constitute payment in full of all such claims and a full release and discharge of Owner from any and all further liability in connection with the subject project.
CHANGE ORDER DETAILS:
Item No. 1 | GC COR 39145: RFI-362 Installing Card Readers in Fire-Rated Door Frames.
Reasons: | C: Errors & Omissions (by the Architect & Design Team)
Item No. 2 | GC COR 39202: Per RFI-385, Perform additional surveying and staking.
Reasons: | B: Unforeseen Conditions
Item No. 3 | GC COR 39205: Per RFI-303R1, replace all concrete screws with stainless steel concrete screws.
Reasons: | C: Errors & Omissions (by the Architect & Design Team)
Item No. 4 | GC COR 39233: Added seismic loop in cold water line.
Reasons: | C: Errors & Omissions (by the Architect & Design Team)
Item No. 5 | GC COR 39158: RFI-139, CCD-033 Fire Alarm at Off-site PIV. CCD-033 added fire alarm modules to monitor off-site PIV. All other work included in COR 39158 was contract work.
Reasons: | C: Errors & Omissions (by the Architect & Design Team)
Item No. 6 | GC COR 39140: FD-056 Contract drawings showed a recess in the south wall of room B-120 due to an existing concrete column. The recess was only about 1" and looked out of place. Solution was to furr out the wall over the concrete column in room B-120.
Reasons: | C: Errors & Omissions (by the Architect & Design Team)
Item No. 7 | GC COR 39152: FD-114 Once the existing guardrails were removed it was noticed that some of the existing embed plates had holes in them and some areas of the existing curbs had significant spalls in the concrete. Solution was to fill any holes in the existing embed plates with epoxy, and sack the damaged curbs which were marked out to be repaired, and paint over the repairs. Cost was never provided by the contractor, so an estimate coordinated with their field and was finalized on their behalf.
Reasons: | B: Unforeseen Conditions
Item No. 8 | GC COR 39169: RFI-412 Intrusion and access control integration changes
Reasons: | C: Errors & Omissions (by the Architect & Design Team)
Item No. 9 | GC COR 39184: FD-116, CCD-034 ADA corrections required by DSA Field Engineer
Reasons: | B: Unforeseen Conditions
Item No. 10 | GC COR 39200: Added 5 additional max occupancy signs per District request.
Reasons: | A-1: District Request
Item No. 11 | GC COR 39209: FD-107. Bulletin #5R2 During coordination of the furniture layouts in Computer labs A-203 and A-207, several changes occurred, which resulted in Bulletin #5R2 being issued requiring additional data drops at each desk, as well as added wiremolds and power poles. Overall there was a reduction in the electrical scope of work with the total number of quad outlets noted for each room being reduced. Additionally in lieu of surface mounted conduits at each data rack that were required per contract, wiremolds were added to be attached on the outside end of each data rack to provide the power and data feeds for students use at each desk, eliminating the need for the conduits in those locations. Cost includes labor and materials for added low voltage, as well as material add for wiremolds.
Reasons: | C: Errors & Omissions (by the Architect & Design Team)
Item No. 12 | GC COR 39219: FD-115 Additional monitoring points added to fire alarm system for DAS, per response to RFI-408.
Reasons: | C: Errors & Omissions (by the Architect & Design Team)
Item No. 13 | RCCD and Soltek Pacific mutually agreed on a negotiated cost credit back to the District, offsetting items 6, 7, 8, 9, 10, 11 and 12.
Reasons: | I: Others: Credit to District
TOTAL ADD/CREDIT:
REVIEWED BY:
DATE:
Facilities and Planning Specialist/Accounting
RECOMMENDED:
DATE:
Name:
Company:
Architect of Record
DATE:
Name:
Company:
Construction Manager
DATE:
Bart L. Doering
RCCD FPD Facilities Development Director
DATE:
Hussain Agah
Associate Vice Chancellor, Facilities Planning & Development
APPROVED BY:
DATE:
Name:
Contractor
DATE:
Aaron S. Brown
Vice Chancellor, Business & Financial Services
Reasons for Change: | A: Owner Request (Added Scope; Design Enhancement; System Improvement; TCO; etc.) A-1 District request; A-2 College request
B: Unforeseen Conditions
C: Errors & Omissions (by the Architect & Design Team)
D: Code Compliance (Code Changes by DSA and other agencies; etc.)
E: Third Party Delay (Federal, State & Local Agencies; Public Owned Utilities; etc.)
F: Unused Construction Allowances
G: Liquidated Damages Assessed
H: Back-charges for deficient work
I: Others -------------------------------------------------